## project WBS monitor
project: | WorkBreakdown Structure (WBS) monitor |  |  | remark | WBS id is reference to chapter in functional design (FD)
calculator: |  |  |  | remark | for FD: chapter are not chronological
date: | 2015-10-16 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | Computer instellen | m | Mboo, Mjak, Rbro | computer crashed | 8
2 |  | apparatuur vast maken aan computer | m | Mboo, Mjak, Rbro | verkeerd aangesloten | 4
3 |  | connection to game | m | Mboo, Mjak, Rbro | instellingen game niet goed | 50
4 |  | python progamma onderzoeken | m | Mboo | begrijpt python niet | 10
5 |  | python progamma klaarmaken voor gebruik | m | Mboo | pyton bugged | 15
6 |  | connection to game | m | Mboo, Mjak, Rbro | geen connectie met game | 15
7 | connection to game | dial speed | m | Mjak | krijgt geen signaal | 5
8 | connection to game | dial for rpm | s | Mjak | krijgt geen signaal | 5
9 |  | TM1683 Onderzoeken en voorbereiden | m | Mboo, Rbro | Begrijpen de theorie niet | 5
10 |  | TM1683 invoegen in arduino progamma | m | Rbro | Library werkt niet | 5
11 | connection to game | display for total race time | c | Rbro | krijgt geen signaal | 2
12 | connection to game | display for round time | c | Rbro | krijgt geen signaal | 2
13 | connection to game | display current place in game | s | Mjak | krijgt geen signaal | 2
14 | connection to game | display round number | s | Mboo | krijgt geen signaal | 2
15 | connection to game | display rpm in leds | m | Rbro | krijgt geen signaal | 2
16 |  | design van handrem maken | s | Mboo, Mjak | kunnen geen fatsoenlijk design maken | 2
17 |  | Handrem fabriceren | s | Mboo, Mjak | teschnishe problemen | 5
18 |  | Schakel pook design maken | s | Mjak, Rbroo | kunnen geen fatsoenlijk design maken | 5
19 |  | Schakel pook fabriceren | s | Mjak, Rbroo | teschnishe problemen | 5
20 |  | dot matrix onderzoeken | s | Rbro | Begrijpen de theorie niet | 3
21 |  | dot matrix invoegen in arduino progamma maken | s | Rbro, Mboo | dot matrix doet het niet | 5
22 |  | Project poster | m | Mboo, Mjak | ziet er slecht en onverzorgd uit | 2
23 |  | verslag afmaken en combineren | m | Rbro | niet voldoende materiaal verzameld | 3
24 |  | Website met download | c | Mboo, Mjak, Rbro | geen host voor website | 10
25 |  | Design maken cockpit (de plaats waar je in zit en de perhipials in zijn geplaats) | s | Mjak | design is te wazig om te begrijpen voor de techniek leerlingen | 2
26 |  | Design doorspreken met Dhr. Kalsbeek | s | Rbro, Mjak | geen tijd voor de afspraak | 1
27 |  | Testen | m | Mboo, Mjak | progamma werkt niet | 3
28 |  | Bedrading fancy maken | m | Mboo, Rbro | is niet fancy genoeg | 2
29
30
31
32
33
|  | total |  |  |  | 180 | 0

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma